## Sheet1
Stakeholder Name/Group | Role/Responsibility | Influence Level (High/Low) | Interest Level (High/Low) | Key Requirements | Engagement Strategy | Frequency of Interaction | Communication Method
Dr. Aftab Khan | Doctor/Diagnosis Heart Condition | High | High | Overbooked Schedules, Lack of diagnostic equipment, Delay in receiving test results and inefficient handoff process | Regular meetings, detailed progress reports | Weekly | Meeting and Emails
Dr.Robert Lee | Doctor/Diagnosis Muscles and bones | High | High | Overbooking, Lack of diagnostic equipment, rarely receives patient progress updates, poor user friendly referral system | Regular meetings, detailed progress reports | Weekly | Meeting and Emails
Rajesh Singh | IT Manager | High | High | scheduling and record management systems are not integrated and hospital network is down | Regular meetings, detailed progress reports | Weekly | Meeting and Emails
Laura Simkov | Software Developer | High | High | Online appointment system lacks user-friendly interfaces and Security vulnerabilities in the legacy systems | Regular meetings, detailed progress reports | Weekly | Meeting and Emails
Hospital leadership | CEO/ Hospital director, Medical director, Chief Operating officer, Senior Management | High | High | Accurate data, Dashboards & Reports, KPIs Alert for critical issues | Share summary level updates, involve them in decision making | Bi-weekly | Dashboards, Bi-weekly reports, review meetings and email summaries
Maria Carter | Appointment Scheduler | High | Low | Double bookings, Limited visibility into doctor's real-time availability, current patient record system outdated and delays in retrieving patient histories during busy hours | Bi-weekly updates and only involve in major decisions | Bi-weekly | Email
Ivan Walker | Billing Administrator | High | Low | Complaints from patients about billing discrepancies , Struggles with reconciling billing records with treatment data from various departments. | Bi-weekly updates and only involve in major decisions | Bi-weekly | Email
Santa Murmu | Pediatric Nurse | Low | High | Uneven nurse-to-patient ratio during night shifts, Limited availability of essential supplies like gloves and syringes, Poor coordination with the emergency department and Rarely receives advance notifications about patient transfers | Regular Updates, share progress reports | Monthly | Newsletters, dashboards, surveys
Jessica Gomes | Emergency Room Nurse | Low | High | Challenges during shift overlaps when resources (e.g., beds, monitors) are in high demand, Inadequate staffing during weekends, delays in receiving diagnostic results from radiology and miscommunication during patient transfers to the ICU | Regular updates , share progress reports | Monthly | Newsletters, dashboards, surveys
Patients | End user | Low | High | Difficulty booking appointments online, Appointments canceled without timely notifications, waits more time to consult doctor, lack of updates during delays, limited infos provided about next step after consultation, For aged patients online appointments are confusing and its difficuilt for them to reach support desk for follow up questions about prescription | Timely notifications about appointments and next step after consultations | Whenever they get the appointment | SMS and via emails
Support Staff | Operational Facilitators | Low | High | Clear task allocation, easy access to patient information, real time notification, simple and user friendly system | Passive updates via meeting notes or reports | As needed | Reports , meeting notes, bilboards