## Sheet1
WBS ID | Task Name | Task Description | Owner | Milestone/Deliverable | Estimated Duration
1 | HealthFirst Care | Root level of Project | PM | Project Kick-Off
1.1 | Requirements Gathering | Define and document project requirements | BA | Requirements document | 1 week
1.1.1 | Stakeholder Interviews | Collect requirements from stakeholders | BA | Stakeholder feedback report | 2 Days
1.1.2 | Data analysis | Analyze provided data files | DA | Data insights document | 3 Days
1.2 | Business Requirement Documentation | Document and structure requirements | BA | brd Completed | 1 week
1.2.1 | Requirement Documentation | Document all collected requirements | BA | Requirements Documentation | 2 days
1.2.2 | Requirement Prioritization | Prioritize requirements | BA | Prioritized Requirements List | 1 day
1.2.3 | Requirement Traceability Matrix | Map requirements to objectives | BA | RTM Document | 2 days
1.3 | Stakeholder Analysis | Identify and analyze stakeholders | BA | Stakeholder Analysis Completed | 1 week
1.3.1 | Stakeholder Identification | Identify stakeholder | BA | Stakeholder List | 1 day
1.3.2 | Stakeholder Analysis | Analyze stakeholder interest and influence | BA | Stakeholder Analysis Report | 1 day
1.3.3 | Stakeholder Engagement Plan | Define engagement strategy | BA | Engagement Plan | 2 days
1.4 | Project Planning | Define and plan project scope | PM | Project Planning Completed | 1 week
1.4.1 | Scope Definition | Define project scope | BA | Scope Document | 1 day
1.4.2 | Scope Management Plan | Document scope management approach | PM | Scope Management Plan | 2 days
1.4.3 | WBS Creation | Break project into tasks | BA | WBS Document | 2 days
1.5 | Process Modeling | Analyze and improve processes | BA | Process Models Completed | 1 week
1.5.1 | Process Analysis | Analyze workflows | BA | Process Analysis Report | 2 days
1.5.2 | AS-IS Process Model | Document current process | BA | AS-IS Diagram | 2 days
1.5.3 | TO-BE Process Model | Design improved process | BA | TO-BE Diagram | 2 days
1.6 | Data Analysis & Visualization | Analyze and visualize data | DA | Dashboard Completed | 1 week
1.6.1 | Data Cleaning | Clean data | DA | Clean dataset | 2 days
1.6.2 | Data Analysis | Analyze trends | DA | Analysis Report | 2 days
1.6.3 | Data Visualization | Create visual reports | DA | Visual Reports | 2 days
1.7 | Risk Assessment | Identify and manage risks | PM | Risk Assessment Completed | 1 week
1.7.1 | Risk Identification | Identify risks | PM | Risk List | 1 day
1.7.2 | Risk Analysis | Analyze risks | PM | Risk Analysis Report | 2 days
1.7.3 | Risk Mitigation | Define mitigation strategies | PM | Mitigation Plan | 2 days
1.8 | Final Presentation | Prepare final output | BA | Project Completed | 1 week
1.8.1 | Presentation Preparation | Create presentation | BA | Presentation Slides | 2 days
1.8.2 | Case Study Summary | Summarize findings | BA | Summary Document | 1 day